## Sheet1 (2)
PROJECT CHARTER
PROJECT NAME |  | DATE | AREA OF FOCUS
NodytCurity: Empowering the Next Generation of Digital Defenders |  |  | Cybersecurity & IT Education
PROBLEM STATEMENT |  | SCOPE
University students are currently the weakest link in campus security, making them vulnerable to phishing and social engineering attacks that put institutional data at risk. Existing security measures are commonly reactive rather than proactive and there is currently no mandatory practical training to turn students into the first line of defense. |  | IN SCOPE |  | Out of Scope
|  | 1. Secure web login module. |  | 1. Native mobile application (Web Responsive only).
|  | 2. Student progress dashboard. |  | 2. Physical server security.
|  | 3.Simulated phishing email engine. |  | 3. IT hardware support for students.
4. Final evaluation quiz.
"SMART" OBJECTIVES |  | HIGH-LEVEL REQUIREMENTS |  | HIGH-LEVEL RISKS
1. Deploy a functional MVP with atleast 5 training modules. |  | 1. Video modules and quiz components |  | 1. Video playback compatibility across different browsers
2. Successfully execute testing of 50 simulated phishing emails with zero delivery errors. |  | 2. Automated phishing email simulations |  | 2. Technical Debt from AI-generated code
3. Successfully integrate dashboard? |  | 3. Administrative dashboard for progress tracking |  | 3. Serves Scalability for large group log ins
PROJECT PURPOSE |  | KEY DELIVERABLES
To develop a centralized and gamified e-learning platform that educates students in cybersecurity best practices and test retentioin of what they have learned via simulated attacks. |  | 1. Project Management Plan: Finalized schedule and scope document. |  | 5. Admin Reporting Module: View for professors/admins to see vulnerability statistics.
|  | 2. Software Requirements Specification (SRS): Document detailing functional and non-functional needs. |  | 6. Training Content: A set of 5 educational quizzes and tip sheets.
|  | 3. Phishing Simulator Engine (MVP): Fully functional backend script to send safe fake emails. |  | 7. Final Deployment Report: Documentation of the cloud setup and user manual.
4. Student Dashboard: Frontend interface for tracking user progress and scores.
BUSINESS CASE |  | ACTION PLAN
Preventing a single data breach saves the university thousands of dollars in recovery costs and reputational damage. This project minimizes human risk through automated, low-cost education compared to the high cost of a real attack. |  | MILESTONES |  | TARGET SCHEDULE
|  | Project Planning & Charter Approval |  | Week 1 - Completed
|  | Team Onboarding & Setup |  | Week 1 - Completed
|  | Requirements Gathering |  | Week 2 - Completed
|  | Architecture & Database Design |  | Week 3 - Completed
|  | Frontend/Backend Development (Sprints) |  | Weeks 4 to 6 - Ongoing
|  | QA & Penetration Testing |  | Week 7 - Pending
|  | Final Launch & Presentation |  | Week 8 - Pending
TEAM MEMBERS |  | FINANCIALS
NAME | FUNCTION | BUSINESS IMPACT |  | INVESTMENT
CESAR MATTA Engineering Project Manager & Owner | System Architecture, Phishing Engine, Security & Encryption, Infrastructure Testing Additional Scope due to Mohammed's re-assignment: Antigravity code remediation, video playback debugging, and UI responsiveness | Implementing this platform will: 1. Reduce Risk: Industry benchmarks suggest that targeted phishing simulations reduce successful attacks by ~70%. 2. Avoid Cost: The average cost of a data breach is $150 per record. By training 1,000 students, the university avoids a potential liability of $150,000 in a single breach event. 3. Add Reputational Capital: Protects the University’s brand and student trust, which is invaluable. |  | 1. Labor (WBS) 90 hours @ $50/hr (Pro bono) Market Value : $ 4,500.00 Actual Cash Cost: $ 0.00 2. Infrastructure VPS Server Hosting & Domain (In-Kind) Market Value : $ 155.00 Actual Cash Cost: $ 0.00 3. Specialized Tools Antigravity Paid Version (Covered by EPM) Market Value: $ 20.00 Actual Cash Cost: $ 0.00 4. Contingency 15% Risk Reserve Market Value: $ 700.00 Actual Cash Cost: $ 0.00 TOTAL PROJECT MARKET VALUE: $ 5, 375.00 NET CASH REQUIRED: $ 0.00
MOHAMMED SHAFEUDDIN Software Quality & UX Engineer | Focuses on Antigravity code remediation, video playback debugging, and UI responsiveness *Re-assigned. Cesar Matta assumed all QA and UI/UX responsibilities
ANDREA BENEDICTO Systems Architect & Lead Analyst | Requirements Mapping, CPM (Critical Path Method), WBS (Work Breakdown Structure), Resource Management, Final Synthesis
KANYKEI OMURBEKOVA Project Controller & Compliance | UI/ UX Design, Risk Management, EVM (Earned Value Management), Compliance, Training Content
ASSUMPTIONS/CONSTRAINTS |  | RISK PLANNING
Constraints 1. Budget: Zero-budget for licenses; must use free/open-source tools. 2. Time: Hard deadline of 8 weeks (Course duration). 3. Tech: Must run on a standard web browser without installing .exe files. |  | 1. Technical Knowledge Silo Risk: Significant project logic resides with the Engineering Core. If a primary dev is unavailable, members responsible for strategy may lack the technical context to push code. Mitigation: Cross document and maintain a shared repository of "Antigravity" prompts and logic. Daily Syncs: Daily GitHub pushes and "vibe-code" reviews to ensure the Analyst wing understands the current build state. 2. VPS Configuration Delays Risk: Excessive time spent securing or configuring the Linux/Ubuntu environment, stalling frontend deployment. Mitigation: Time-box setup to 48 hours max. Immediate fallback to a Localhost demonstration if Port 80/443 issues persist beyond the grace period. 3. 8-Week Deadline Crunch Risk Running out of time for testing. Complexities in video playback or phishing logic may consume allocated testing period. Mitigation: Drop "Admin Reporting" feature if behind schedule. Prioritize functional Phishing Simulator above all else.
Assumptions: 1. Students have high-speed internet access; "Antigravity" tool will resolve video bugs. 2. The personal VPS is already configured with Linux/Ubuntu and has open ports (80/443) for web traffic. 3. The University network will allow access to the VPS IP address without blocking it. 4. Open-source libraries are approved for use.

## Sheet1 (hidden)
PROJECT CHARTER
PROJECT NAME |  | DATE | AREA OF FOCUS
E-niche commerce product selection database |  | 2019-09-13 | E-niche commerce for Baby product selection database
BUSINESS CASE |  | SCOPE
Product Research Team is critically important in deciding the product e-niche that the organization wants to do business in. This project will implement the Product Research Team that will (1) research on tools like Junglescout and Helium10 (2) scavenge for good products on forums like Facebook Communities & Amazon, and (3) decide on the best possible descriptions and pricing for the products |  | IN SCOPE | IN SCOPE | OUT OF SCOPE
|  | Baby Pillows | Baby Books | Baby Food Products
|  | Baby Travel Products | Baby Wipes
Camping Products
KEY DELIVERABLES
|  | Proposed Organization Chart | Training & Orientation Module
|  | Approved Organization Chart | Finalized JD & Task List
|  | Approved Budget | prototype data pase
Team on Board
Standard Operating Procedures
MEASURABLE TARGET/GOAL |  | TIMELINE
Finalize Logo | 2019-09-25 | ACTIONS/MILESTONES |  | TARGET DATE/STATUS
Bring HR on board | 2019-09-27 | Develop Org Chart & Hierarchy Level |  | 2019-09-20
Develop Descriptions | 2019-09-29 | Budget & Team Approval Meeting |  | 2019-09-22
Bring a Consultancy on Board | 2019-09-30 | Job Posting Setup Internally & On Job Portals |  | 2019-09-25
|  | Interview Process for Amazon Specialist |  | 9/26/2019-10/15/2019
|  | Amazon Specialist Hired |  | 2019-10-17
|  | Other Positions Filled |  | 2019-10-20
|  | Orientation |  | 2019-10-22
TEAM MEMBERS |  | Team Members Join The Floor |  | 2019-10-25
NAME | FUNCTION
Aaditya Shah | Marketing
Ishita Kotak | R&D
Rohit Sadh | Human Resources | FINANCIALS
Solomon John | Import/Export | BUSINESS IMPACT |  | INVESTMENT
Prastin Paul | Packaging | Ensure smooth and easy penetration into the baby segment market on Amazon & ensuring profit margin of 30% on monthly basis |  | Rolling Expense: $100k
ASSUMPTIONS/CONSTRAINTS |  | RISK PLANNING
Team must be on board by 10/25/2019 and fully functional |  | This project requires an individual with in-depth experience of selling on Amazon. The project requires an individual with minimum 8 years of work experience and hence bringing such an individual on board would be critical - reseaech more risk involve ?????
$100k rolling capital